## Sheet1
Requirements | Status | Completion date | Comments
discounting in the system as per prices. | Done | 2017-06-01
determine retail price, whole sale price and traders price. | Done | 2017-06-01
Additional tab for sales – rep with commission | Not Started
Sales order – status: Paid(fully paid), received(not yet paid) | Not Started
Supplier look up | Done | 2017-05-01
Per supplier look up from product | Done | 2017-05-01
Tagging of active and inactive customers | Not Started
Printing setup | Not Started |  | Not on initial Discussion
Selling price – price cost – profit of business. | Not Started |  | Not on initial Discussion
Customer Tab Contact person, Multiple contact person, fax and image | Not Started
Supplier Tabe - Product from supplier, Name, Address, Contact number Contact person | Done | 2017-05-01
Product Tab - Image, on unit measurement drop down please include: Bags, box, gallons, caddie, ML, bundle, bottles, hanks, sticks, barrel, roll and piece - Traders price change it to Resellers price - add another whole sale price text box, name it as whole sale price 1 and whole sale price 2 | Done | 2017-06-01 | Added functionality of another 1 textbox
Order Tab - On the date, the default day should be populated but can be change accordingly - Add unit of measurement - On the type of order please add via text, via email, via salesrep, via online | Done | 2017-06-01 | Added functionality salesrep, and unit of measurement
Add tab for Purchase order | Done | 2017-05-01
Mirror the purchase orders tab from Add products | Not Started
Price should be depending on the last transaction history | Done | 2017-07-01
Add tax on order form | Done | 2017-07-01
Order price should by editable | Done | 2017-07-01
Add mark up value on products | Not Started
Change ORDER to SALES ORDER | Not Started
Add WORK ORDER Tab | Done | 2017-07-01
DASHBOARD functionalities | In-progress
Admin and User distinctions | Not Started
Validations per Tab (eg. Numeric, alpha numeric) | Not Started
Date/Time on the system | Done | 2017-05-01
Check statuses (Bounce, fully paid) | Not Started